## Sheet1
Db Create and update | 1 day
Add/Update Advertisment Screen Modification(DB,Angular and Api) | 1/2 day
Adv List screen modification Acc. to discussion(Status update with Sending Notification) (DB,Angular and Api) | 2 days
New Screen For Upload Re-design of Advertisement by platform users(DB,Angular and Api) | 1 day
New Screen of List of Re-design for Admin (DB,Angular and Api) | 1/2 day
New screen of show Re-design Details for admin where admin will take action of Approve and reject(DB,Angular and Api) | 1/2 day
New screen for download Advertisement and see detail of advertisement | 1 day
Screen For CategoryMaster with CRUD operation (DB,Angular and Api) | 1/2 day
Screen For SubCategoryMaster with CRUD operation (DB,Angular and Api) | 1/2 day
Screen For PlatformMaster with CRUD operation (DB,Angular and Api) | 1/2 day
Screen For NotificationMaster with CRUD operation (DB,Angular and Api) | 1/2 day
Screen For ApprovalDetailMaster with CRUD operation (DB,Angular and Api) | 1 day
Email Template for notify Department | 2 days Statis for now
SMS Template for notify Department
Email Template for notify unapproved plateform user
SMS Template for notify unapproved plateform user
Email Template for notify approved plateform user
SMS Template for notify approved plateform user
Scheduler for Notify plateform users ,Admin and Our portal's NotificationMaster | 3 days
Web services for mark as complete (after upload adv on thier portel by plateform user) | 1/2 day
Meeting at CMO(Scheme, order and Adv query) | 5 hrs | 2019-09-06