## Sheet1
Advertisement Notification screen (Angular+API) | 1 day
Dynamic Mail Template(Angular +Api+ All places where we are sending email) | 2 days
Dynamic SMS Template(Angular +Api+ All places where we are sending sms) | 2 days
User Advertisement List+Advertisement List Screen Publish section functionality | 3/2 day
Service For Download Advertisement By Date | 1 day
Advertisement Raw Data | 1/2 day
Advertisement Add Screen: | 1/2 day
User Re-Design Screen + Admin Re-Design Screen (Angular +Api+Db changes) | 3/2day
Advertisement Scheduler modification | 2 days
Done
User Advertisement List
Advertisement Notification screen (Angular+API)
Service For Download Advertisement By Date
User Re-Design Screen + Admin Re-Design Screen (Angular +Api+Db changes)
User Advertisement List+Advertisement List Screen Publish section functionality