## Sheet1
DB Changes | 1.5 days
Service Implementation
modification in Add Api | 1.5 days
modification in update Api | 1/2 day
modification in List Api | 1 day
modification in Details Api
modification in Delete Api
Scheme master in api | 1/2 day | 2019-09-16
Scheme type master in api |  | 2019-09-16
Scheme upload file category master. |  | Done
Scheme required document category master.
Scheme category master.
Scheme beneficial category master
Scheme output master
Scheme type master
Monitoring parameters master | 1/2 day
Scheme Parameter Mapping | 1 day
Scheme Data Entry Screen | 2 days
Screen Time
modification in Add | 1.5 day
modification in update | 1 day
modification in List | 1 day
modification in Details
modification in Delete
Scheme master in angular | 1/2 day | 2019-09-16
scheme type master in angular |  | 2019-09-16
Scheme upload file category master. |  | Done
Scheme required document category master.
Scheme category master.
Scheme beneficial category master
Scheme output master
Scheme type master
Monitoring parameters master | 1/2 day
Scheme Parameter Mapping | 1 day
Scheme Data Entry Screen | 2 days