## Sheet1
DB Changes | 2 days
Service Implementation
modification in Add Api | 1 day | 2019-09-23
modification in update Api | 1 day
modification in List Api | 1/2 day
modification in Details Api | 1/2 day
modification in Delete Api
Scheme upload file category master. | 1/2 day | 2019-09-16
Scheme required document category master. | 1/2 day
Scheme category master. | 1/2 day
Scheme beneficial category master | 1/2 day
Scheme output master | 1/2 day
Scheme type master | 1/2 day
Monitoring parameters master | 1 day | 2019-09-30
Scheme Parameter Mapping | 1 day |  | tanmaya
Scheme Data Entry Screen | 2 days |  | paras
paras
Screen Time
modification in Add | 1 day | 2019-09-23
modification in update | 1/2 day
modification in List | 1/2 day
modification in Details | 1/2 day
modification in Delete
Scheme upload file category master. | 4 days | 2019-09-16
Scheme required document category master.
Scheme category master.
Scheme beneficial category master
Scheme output master
Scheme type master
Monitoring parameters master | 1 day | 2019-09-30
Scheme Parameter Mapping | 1 day
Scheme Data Entry Screen | 2 days